## Settings
Counterpart MVP — Plan Settings (Revised)
Edit values in column B. The plan is now scoped around memory + summary + logging, not the full classifier. Dates compute from start date.
Setting | Value | Notes
Plan start date | 2026-05-11 | First working day.
Working days per week | 5 | 5 = mon-fri, 6 = include sat, 7 = include sun.
Hours per working day | 8 | Realistic hours of focused work per day.
Skip weekends | TRUE | TRUE = saturdays and sundays non-working.
Founder solo | TRUE | TRUE = solo. FALSE = adjust task estimates.
Apply to YC | TRUE | TRUE = include YC application milestones.
Target launch day | 30 | Working day number of public launch.
Buffer days at end | 5 | Slippage absorption between core build done and launch.
Workstream legend
Build | Engineering — product, logging, summarization
Marketing | Content, social, audience, founder voice
Research | User interviews, evals, prompt iteration
Ops | Setup, accounts, legal, admin, money
What changed from previous version
1. Personalization is now memory + summary, not full classifier. Saves ~10 days.
2. Behavioral logging is now richer — Tier 1 of data collection doc fully implemented at MVP.
3. Onboarding is more thorough — five forced-choice questions + free text + initial summary generation.
4. Profile transparency UI is now first-class, not a final-week add-on.
5. Phase 2 components (full classifier, Bayesian filter, etc.) are deferred until data shows they're needed.
6. The full classifier plan and prompts document are still valid as Phase 2 reference material.

## Day Plan
Counterpart MVP — Day-by-Day Plan (Revised)
Total tasks | 95 | Tasks done | 0 | Progress | 0% | Total hours | 281 | Hours done | 0 | Target launch | 2026-06-19
Day | Date | Phase | Workstream | Task | Why this matters | Depends on | Hours | Working | Notes | Blocks | Done
1 | 2026-05-11 | 1 — Foundations | Ops | Generate 30-50 candidate product names. Run trademark + domain checks on top 10 | Counterpart name has trademark conflict; rename before any public launch |  | 4 | TRUE |  |  | FALSE
1 | 2026-05-11 | 1 — Foundations | Ops | Create accounts: GitHub, Vercel, Supabase, Anthropic API, Voyage AI | Foundation infrastructure |  | 2 | TRUE |  |  | FALSE
1 | 2026-05-11 | 1 — Foundations | Marketing | Read principles + branding + data collection docs. Draft positioning | Lead with personalization, not anti-sycophancy |  | 2 | TRUE |  |  | FALSE
2 | 2026-05-12 | 1 — Foundations | Ops | Email UK trademark attorney for clearance opinion on top 3 names (£300-700) | Cheaper than later rebrand | 1 | 1 | TRUE |  |  | FALSE
2 | 2026-05-12 | 1 — Foundations | Build | Initialize Next.js 14 + TypeScript + Tailwind + shadcn/ui app. Push to GitHub | Frontend scaffold | 1 | 3 | TRUE |  |  | FALSE
2 | 2026-05-12 | 1 — Foundations | Build | Set up Codespaces config (.devcontainer) with Claude Code installed | Cross-device dev | 1 | 1 | TRUE |  |  | FALSE
2 | 2026-05-12 | 1 — Foundations | Marketing | Set up X account, write profile bio, post intro thread | Audience-building takes 3-6 months. Start now |  | 1 | TRUE |  |  | FALSE
2 | 2026-05-12 | 1 — Foundations | Marketing | Buy domain + reserve handles for top 3 candidate names | Lock identity before final decision | 2 | 1 | TRUE |  |  | FALSE
3 | 2026-05-13 | 1 — Foundations | Build | Build schema: users, sessions, messages, response_pairs, onboarding_responses, user_profiles, events tables | Schema from data collection doc § 2. Comprehensive from day 1 | 2 | 5 | TRUE |  |  | FALSE
3 | 2026-05-13 | 1 — Foundations | Build | Wire up Supabase Auth (email magic link or Google SSO) | Need user identity for any personalization | 3 | 2 | TRUE |  |  | FALSE
3 | 2026-05-13 | 1 — Foundations | Marketing | Build landing page v1: hero + 3 proof points + email capture | Start collecting emails immediately |  | 1 | TRUE |  |  | FALSE
4 | 2026-05-14 | 1 — Foundations | Build | Build minimal chat loop: input → API → Claude Sonnet → display. Working end-to-end | Working product. Foundation for everything | 3 | 4 | TRUE |  |  | FALSE
4 | 2026-05-14 | 1 — Foundations | Build | Implement comprehensive message logging: every user + assistant message with all linguistic features | Tier 1 logging from data collection doc. Non-negotiable from day 1 | 4 | 3 | TRUE |  |  | FALSE
4 | 2026-05-14 | 1 — Foundations | Marketing | Submit landing page to Indie Hackers; share on personal X | Tiny early audience signal | 3 | 1 | TRUE |  |  | FALSE
5 | 2026-05-15 | 1 — Foundations | Build | Implement response_pairs table population: regenerate, time-to-followup, copy detection | The relationship layer. Most analytical questions answered from this table later | 4 | 5 | TRUE |  |  | FALSE
5 | 2026-05-15 | 1 — Foundations | Build | Implement session creation, close detection, basic session metrics | Sessions are the unit of analysis for retention | 4 | 2 | TRUE |  |  | FALSE
5 | 2026-05-15 | 1 — Foundations | Marketing | Write manifesto essay v1: 'The personal AI thesis' | Long-form artifact for newsletters, HN, YC. Cross-post X+LinkedIn |  | 1 | TRUE |  |  | FALSE
6 | 2026-05-18 | 1 — Foundations | Ops | Write privacy policy + terms of service (Termly or fiverr lawyer) | Privacy posture is a brand feature |  | 2 | TRUE |  |  | FALSE
6 | 2026-05-18 | 1 — Foundations | Build | Set up PostHog analytics, instrument basic frontend events | Behavioral signals + product analytics are different. Need both | 5 | 2 | TRUE |  |  | FALSE
6 | 2026-05-18 | 1 — Foundations | Build | Deploy to Vercel; verify chat loop and logging work in production | Local-only doesn't count | 5 | 1 | TRUE |  |  | FALSE
6 | 2026-05-18 | 1 — Foundations | Marketing | Publish manifesto essay. Cross-post X thread + LinkedIn | First major content artifact | 5 | 2 | TRUE |  |  | FALSE
6 | 2026-05-18 | 1 — Foundations | Marketing | First X build-in-public post with screenshot | Establish cadence | 6 | 1 | TRUE |  |  | FALSE
7 | 2026-05-19 | 1 — Foundations | Build | Buffer day: catch up on Phase 1 slippage, refactor, fix bugs | Always slippage. Better to absorb than push forward |  | 6 | TRUE |  |  | FALSE
7 | 2026-05-19 | 1 — Foundations | Marketing | Reply to manifesto comments + X thread engagement | 48h engagement window is critical | 6 | 2 | TRUE |  |  | FALSE
8 | 2026-05-20 | 2 — Personalization layer | Build | Build onboarding UI: 5 forced-choice questions + 3 free-text fields with timing capture | Onboarding is the moment users feel personalization first. Critical UX | 7 | 6 | TRUE |  |  | FALSE
8 | 2026-05-20 | 2 — Personalization layer | Build | Capture choice durations on frontend (decision speed signal) | Fast choice = confident, slow = deliberation | 8 | 2 | TRUE |  |  | FALSE
9 | 2026-05-21 | 2 — Personalization layer | Build | Implement initial profile summary generation: Haiku call from onboarding inputs | First profile = first impression. Has to be good | 8 | 3 | TRUE |  |  | FALSE
9 | 2026-05-21 | 2 — Personalization layer | Build | Build user_profiles table with versioning (is_current, version columns) | Old summaries kept for analysis; never overwrite | 9 | 2 | TRUE |  |  | FALSE
9 | 2026-05-21 | 2 — Personalization layer | Build | Wire system prompt composer: base + user_summary + session_context | Where personalization actually shows up in responses | 10 | 3 | TRUE |  |  | FALSE
10 | 2026-05-22 | 2 — Personalization layer | Build | Implement A/B cohort assignment at signup (with-personalization vs without) | Without this, can't validate that personalization works. CRITICAL non-negotiable | 11 | 3 | TRUE |  |  | FALSE
10 | 2026-05-22 | 2 — Personalization layer | Build | Wire cohort into system prompt composer (without-cohort gets base instruction only) | Control group sees generic AI. The comparison is the validation | 12 | 2 | TRUE |  |  | FALSE
10 | 2026-05-22 | 2 — Personalization layer | Build | Log cohort_at_generation on every response_pair | Snapshots for future analysis. Must be in row at write time | 12 | 1 | TRUE |  |  | FALSE
10 | 2026-05-22 | 2 — Personalization layer | Marketing | Daily X post: build-in-public update on architecture | Cadence |  | 1 | TRUE |  |  | FALSE
11 | 2026-05-25 | 2 — Personalization layer | Build | Build session_close detection background job (5min cadence, 30min idle threshold) | Sessions close themselves; don't depend on user explicit action | 10 | 3 | TRUE |  |  | FALSE
11 | 2026-05-25 | 2 — Personalization layer | Build | Implement summarization job: load profile + session, call Haiku, write new version | The compounding personalization mechanism. Heart of the MVP | 13 | 4 | TRUE |  |  | FALSE
12 | 2026-05-26 | 2 — Personalization layer | Build | Frontend typing instrumentation: typing_started_at, typing_duration, edit_count, paste_event_count | Tier 2 logging. Reveals cognitive load patterns | 11 | 4 | TRUE |  |  | FALSE
12 | 2026-05-26 | 2 — Personalization layer | Build | Frontend scroll/read instrumentation on responses | Reading depth is high-signal for response quality | 15 | 3 | TRUE |  |  | FALSE
12 | 2026-05-26 | 2 — Personalization layer | Build | Page visibility events (count tab switches, don't track destination) | Distraction proxy without surveillance | 15 | 1 | TRUE |  |  | FALSE
13 | 2026-05-27 | 2 — Personalization layer | Build | Integrate Voyage AI embeddings, populate messages.embedding asynchronously | Embedding is substrate for retrieval and clustering | 11 | 3 | TRUE |  |  | FALSE
13 | 2026-05-27 | 2 — Personalization layer | Build | Build retrieval function: k=5 most similar past messages for current user | Per-user few-shot context for response generation | 18 | 3 | TRUE |  |  | FALSE
13 | 2026-05-27 | 2 — Personalization layer | Build | Wire retrieval into system prompt composer (optional context block) | Personalization through history retrieval | 19 | 2 | TRUE |  |  | FALSE
14 | 2026-05-28 | 2 — Personalization layer | Build | Build background jobs: 24h/7d/30d return checks, topic shift computation | Outcome signals only fillable async. Schedule them now | 5,11 | 4 | TRUE |  |  | FALSE
14 | 2026-05-28 | 2 — Personalization layer | Build | Build user_aggregates nightly rollup job | Per-user metrics for retention analysis | 20 | 3 | TRUE |  |  | FALSE
14 | 2026-05-28 | 2 — Personalization layer | Marketing | Weekly X thread: 'building the data layer for a personal AI' | Show engineering depth |  | 1 | TRUE |  |  | FALSE
15 | 2026-05-29 | 2 — Personalization layer | Research | End-to-end test: create user, complete onboarding, run 50 messages, verify all logging fields populate correctly | Catch logging bugs before users do. Bad data is worse than no data | 21 | 5 | TRUE |  |  | FALSE
15 | 2026-05-29 | 2 — Personalization layer | Build | Bug fixes from end-to-end test | Always issues. Fix now while it's still simple | 22 | 3 | TRUE |  |  | FALSE
16 | 2026-06-01 | 3 — Polish + onboarding | Build | Build 'My Data' panel: view profile summary, edit it, view conversation history | Privacy posture is a brand feature. Users always know what's stored | 22 | 6 | TRUE |  |  | FALSE
16 | 2026-06-01 | 3 — Polish + onboarding | Marketing | Daily X post: showing the profile transparency UI | Differentiator vs ChatGPT — show, don't tell |  | 2 | TRUE |  |  | FALSE
17 | 2026-06-02 | 3 — Polish + onboarding | Build | Implement end-to-end account deletion (cascade through messages, embeddings, profiles, response_pairs) | GDPR right-to-erasure must work. Non-negotiable | 23 | 5 | TRUE |  |  | FALSE
17 | 2026-06-02 | 3 — Polish + onboarding | Build | Test deletion thoroughly: nothing left behind | Audit trail for deletion is itself sensitive | 24 | 2 | TRUE |  |  | FALSE
17 | 2026-06-02 | 3 — Polish + onboarding | Ops | Buffer / admin | Catch up on accounts, invoices |  | 1 | TRUE |  |  | FALSE
18 | 2026-06-03 | 3 — Polish + onboarding | Build | Build the 10-message profile preview: 'here's what Counterpart understands about you' | Compounding-value moment. Users need to see personalization working | 23 | 4 | TRUE |  |  | FALSE
18 | 2026-06-03 | 3 — Polish + onboarding | Build | Onboarding polish: progress indicators, animation, 'why we ask' explanations | Onboarding completion rate matters for activation | 24 | 4 | TRUE |  |  | FALSE
19 | 2026-06-04 | 3 — Polish + onboarding | Research | Onboard 5 alpha users. 30-min walkthrough each. Notes from every session | Real humans on real product before launch | 26 | 6 | TRUE |  |  | FALSE
19 | 2026-06-04 | 3 — Polish + onboarding | Marketing | Write essay v2: 'What I've learned from 5 users in 30 days' | Honest essays build credibility | 27 | 2 | TRUE |  |  | FALSE
20 | 2026-06-05 | 3 — Polish + onboarding | Build | Bug-fix sprint from alpha sessions: top 5 issues | Always issues. Fix the worst before scale | 27 | 6 | TRUE |  |  | FALSE
20 | 2026-06-05 | 3 — Polish + onboarding | Marketing | Publish essay v2; reply to comments | Engagement window after publishing | 27 | 2 | TRUE |  |  | FALSE
21 | 2026-06-08 | 3 — Polish + onboarding | Marketing | Record 5 demo videos: 30-60s clips showing personalization in action | Highest-ROI content. Show the difference vs ChatGPT in 30 seconds | 28 | 5 | TRUE |  |  | FALSE
21 | 2026-06-08 | 3 — Polish + onboarding | Marketing | Update landing page v2: real user quotes + best demo video | Real quotes always beat marketing copy | 29 | 3 | TRUE |  |  | FALSE
22 | 2026-06-09 | 4 — Pre-launch | Build | Add retry logic, error handling, graceful degradation | Production needs to survive API failures | 28 | 4 | TRUE |  |  | FALSE
22 | 2026-06-09 | 4 — Pre-launch | Build | Set up Sentry for errors + simple metrics dashboard | Can't fix what you can't see | 30 | 2 | TRUE |  |  | FALSE
22 | 2026-06-09 | 4 — Pre-launch | Build | Load test: simulate 100 concurrent users | Launch surge will be larger than current capacity | 30 | 2 | TRUE |  |  | FALSE
23 | 2026-06-10 | 4 — Pre-launch | Build | Implement free tier limits (e.g. 30 messages/day) and Stripe upgrade flow | Free for data, premium for committed users | 31 | 5 | TRUE |  |  | FALSE
23 | 2026-06-10 | 4 — Pre-launch | Build | Build founders' cohort badge for first 1000 users | FOMO without slowing acquisition | 32 | 3 | TRUE |  |  | FALSE
24 | 2026-06-11 | 4 — Pre-launch | Marketing | Write Show HN post + draft Product Hunt launch copy | Coordinated launch needs prep |  | 3 | TRUE |  |  | FALSE
24 | 2026-06-11 | 4 — Pre-launch | Marketing | Reach out to AI/productivity creators for early access | Independent creator coverage worth 10x paid placement |  | 3 | TRUE |  |  | FALSE
24 | 2026-06-11 | 4 — Pre-launch | Marketing | Schedule launch week posts in Typefully | Don't write copy during launch week |  | 2 | TRUE |  |  | FALSE
25 | 2026-06-12 | 4 — Pre-launch | Ops | Final privacy audit: profile delete works end-to-end including embeddings | Non-negotiable | 33 | 3 | TRUE |  |  | FALSE
25 | 2026-06-12 | 4 — Pre-launch | Research | Internal QA pass on 50 test conversations across user types | Catch embarrassing edge cases before public users do | 33 | 4 | TRUE |  |  | FALSE
25 | 2026-06-12 | 4 — Pre-launch | Build | Verify cohort assignment recorded for every new user | If cohorts aren't assigned, validation thesis is unverifiable | 33 | 1 | TRUE |  |  | FALSE
26 | 2026-06-15 | 4 — Pre-launch | Build | Final buffer day: blockers, last polish | Always need a buffer day before launch | 34 | 5 | TRUE |  |  | FALSE
26 | 2026-06-15 | 4 — Pre-launch | Marketing | Email signups list: launch tomorrow | Email list is the warmest channel | 34 | 2 | TRUE |  |  | FALSE
26 | 2026-06-15 | 4 — Pre-launch | Ops | Sleep early, hydrate, eat real food | Launch day is intense |  | 1 | TRUE |  |  | FALSE
27 | 2026-06-16 | 4 — Pre-launch | Build | Buffer / final polish | Last chance before launch | 35 | 6 | TRUE |  |  | FALSE
27 | 2026-06-16 | 4 — Pre-launch | Marketing | Final pre-launch X thread: 'tomorrow we ship' | Build anticipation |  | 2 | TRUE |  |  | FALSE
28 | 2026-06-17 | 4 — Pre-launch | Build | Final tests of everything end-to-end | Launch confidence | 37 | 6 | TRUE |  |  | FALSE
28 | 2026-06-17 | 4 — Pre-launch | Marketing | Pre-launch DM blitz to engaged followers | Soft warm-up for launch day audience |  | 2 | TRUE |  |  | FALSE
29 | 2026-06-18 | 4 — Pre-launch | Build | Day-of-launch checklist: monitoring active, error alerts on, scaling plans ready | If anything breaks during launch, you need to know fast | 39 | 4 | TRUE |  |  | FALSE
29 | 2026-06-18 | 4 — Pre-launch | Marketing | Final scheduled posts confirmed; prepare for live engagement | Pre-prepare so launch day is just engagement | 39 | 4 | TRUE |  |  | FALSE
30 | 2026-06-19 | 4 — Pre-launch | Marketing | LAUNCH: Product Hunt, Show HN, X thread, email list announcement | MVP is live. Real data from here | 40 | 6 | TRUE |  |  | FALSE
30 | 2026-06-19 | 4 — Pre-launch | Marketing | Reply to every comment, DM, HN thread | Engagement window critical | 41 | 4 | TRUE |  |  | FALSE
31 | 2026-06-22 | 5 — Post-launch | Marketing | Continue replying to launch engagement | 48h window | 41 | 4 | TRUE |  |  | FALSE
31 | 2026-06-22 | 5 — Post-launch | Research | Daily review of behavioral signals. Identify top 3 issues | Real data finally. Use it | 41 | 3 | TRUE |  |  | FALSE
31 | 2026-06-22 | 5 — Post-launch | Build | Hot-fix sprint: top issues from launch users | Always issues | 42 | 3 | TRUE |  |  | FALSE
32 | 2026-06-23 | 5 — Post-launch | Build | Continue hot fixes | Stabilize first | 42 | 4 | TRUE |  |  | FALSE
32 | 2026-06-23 | 5 — Post-launch | Research | Personal email to first 50 users for 15-min feedback call | Talking to users beats reading metrics | 42 | 2 | TRUE |  |  | FALSE
32 | 2026-06-23 | 5 — Post-launch | Marketing | X post: '24h after launch, here's what happened' | Transparency builds trust | 42 | 2 | TRUE |  |  | FALSE
33 | 2026-06-24 | 5 — Post-launch | Ops | Finalize YC application using real launch data and retention numbers | Real users + retention data > polished pitch | 43 | 5 | TRUE |  |  | FALSE
33 | 2026-06-24 | 5 — Post-launch | Marketing | Reach out to AI newsletters for feature: Lenny's, Every, Ben's Bites | Newsletter feature drives 1k-10k signups |  | 2 | TRUE |  |  | FALSE
33 | 2026-06-24 | 5 — Post-launch | Research | First feedback call with launch user | Direct conversation | 43 | 1 | TRUE |  |  | FALSE
34 | 2026-06-25 | 5 — Post-launch | Marketing | Write 'launch week recap' essay: numbers, surprises, what's next | Numbers good or bad. Honesty compounds | 44 | 3 | TRUE |  |  | FALSE
34 | 2026-06-25 | 5 — Post-launch | Research | First retention SQL queries: D1 returns by cohort, response pair patterns | Start the analysis loop. Data is finally there | 44 | 3 | TRUE |  |  | FALSE
34 | 2026-06-25 | 5 — Post-launch | Research | More feedback calls | Pattern emerges around call 5-10 | 44 | 2 | TRUE |  |  | FALSE
35 | 2026-06-26 | 5 — Post-launch | Build | Address whatever the data says is the biggest problem | Iteration mode based on real data | 45 | 5 | TRUE |  |  | FALSE
35 | 2026-06-26 | 5 — Post-launch | Marketing | Write next thought piece based on what's emerging from data | Thought leadership compounds | 45 | 2 | TRUE |  |  | FALSE
35 | 2026-06-26 | 5 — Post-launch | Research | Decide what Phase 2 work the data is calling for | Triggers from principles doc § 6 — does cold-start retention need fixing? Etc. | 45 | 1 | TRUE |  |  | FALSE
Formulas:
Date = IF(Settings!$B9=TRUE(),WORKDAY(Settings!$B6-1,[Day]),Settings!$B6+[Day]-1)
Note on A6: Day number from start. Multiple tasks can share a day.
Note on B6: Auto-computed from start date in Settings.
Note on G6: Comma-separated day numbers that must complete before this task.
Note on I6: Set FALSE to skip without deleting.
Note on L6: Mark TRUE when complete.

## Workstreams
Workstreams Summary
Counts auto-update from Day Plan.
Workstream | Tasks | Done | Hours total | % Complete
Build | 49 | 0 | 166 | 0%
Marketing | 30 | 0 | 69 | 0%
Research | 9 | 0 | 27 | 0%
Ops | 8 | 0 | 19 | 0%
Total | 96 | 0 | 281 | 0%
By phase
Phase | Tasks | Done | Hours | % Complete
1 — Foundations | 24 | 0 | 55 | 0%
2 — Personalization layer | 22 | 0 | 62 | 0%
3 — Polish + onboarding | 13 | 0 | 48 | 0%
4 — Pre-launch | 22 | 0 | 74 | 0%
5 — Post-launch | 15 | 0 | 42 | 0%
Hours per day
Day | Hours | Tasks | Tasks done | % complete
1 | 8 | 3 | 0 | 0%
2 | 7 | 5 | 0 | 0%
3 | 8 | 3 | 0 | 0%
4 | 8 | 3 | 0 | 0%
5 | 8 | 3 | 0 | 0%
6 | 8 | 5 | 0 | 0%
7 | 8 | 2 | 0 | 0%
8 | 8 | 2 | 0 | 0%
9 | 8 | 3 | 0 | 0%
10 | 7 | 4 | 0 | 0%
11 | 7 | 2 | 0 | 0%
12 | 8 | 3 | 0 | 0%
13 | 8 | 3 | 0 | 0%
14 | 8 | 3 | 0 | 0%
15 | 8 | 2 | 0 | 0%
16 | 8 | 2 | 0 | 0%
17 | 8 | 3 | 0 | 0%
18 | 8 | 2 | 0 | 0%
19 | 8 | 2 | 0 | 0%
20 | 8 | 2 | 0 | 0%
21 | 8 | 2 | 0 | 0%
22 | 8 | 3 | 0 | 0%
23 | 8 | 2 | 0 | 0%
24 | 8 | 3 | 0 | 0%
25 | 8 | 3 | 0 | 0%
26 | 8 | 3 | 0 | 0%
27 | 8 | 2 | 0 | 0%
28 | 8 | 2 | 0 | 0%
29 | 8 | 2 | 0 | 0%
30 | 10 | 2 | 0 | 0%
31 | 10 | 3 | 0 | 0%
32 | 8 | 3 | 0 | 0%
33 | 8 | 3 | 0 | 0%
34 | 8 | 3 | 0 | 0%
35 | 8 | 3 | 0 | 0%

## Risk Register
Risk Register
Things that could derail the plan.
Risk | Probability (1-5) | Severity (1-5) | Score | Mitigation
Trademark clearance fails on candidate names | 3 | 4 | 12 | Generate 50+ candidates upfront. Have backups.
Anthropic API rate limits during build | 2 | 3 | 6 | Retry/exponential backoff. Cache aggressively.
Cold-start retention < 20% | 4 | 4 | 16 | Onboarding loop and 10-message preview address this.
Personalization cohort doesn't beat control | 4 | 4 | 16 | Honor the data. Maybe the summary needs to be richer, or the system prompt composition needs work. Iterate before assuming the thesis is wrong.
Feature creep slows launch beyond day 30 | 4 | 3 | 12 | Buffer days absorb 1 week. Beyond that, cut scope.
Founder burnout from solo pace | 3 | 5 | 15 | 5 days/week not 7. Recover on weekends.
Privacy bug — user data leaks or delete fails | 2 | 5 | 10 | Day 25 privacy audit non-negotiable.
Summarization job produces bad summaries | 3 | 3 | 9 | Test prompt thoroughly before launch. Manual review of 50 summaries.
Behavioral logging has bugs corrupting data | 3 | 4 | 12 | Day 15 end-to-end test catches this. Bad data is worse than no data.
Mem0 or Supabase service issues at scale | 2 | 3 | 6 | Free tiers tested at small scale. Have fallback plans.

## Decision Log
Decision Log
Use this whenever you make a real decision.
Date | Decision | Why | What changed in plan